## Test plan for YallaKora mobile
Yallakora Test Plan
Mobile Application | Yallakora
version | 1.54
device OS | Android
Author | Mohamed Abd-Elghfar
objective | assess quality & gain confidence
scope | main pages: "الرئيسية","مباريات","بطولات","فرقك","اخبار"
Test Scenario | validate that main pages buttons are working well
check "matches of today" on "main" page
check "news" on "main" page
check match status
check the result of the match
check team/country profile
validate that addition function for team or country is working
check match details
check "latest news " on "news"
check "another sports " on "news"
check notifications of the app
Test execution order | TC_01_الرئيسية
TC_02_الرئيسية
TC_03_الرئيسية
TC_04_الرئيسية
TC_05_الرئيسية
TC_06_الرئيسية
TC_01_مباريات
TC_02_مباريات
TC_03_مباريات
TC_04_مباريات
TC_01_بطولات
TC_01_فرقك
TC_01_اخبار
TC_02_اخبار
TC_07_الرئيسية
TC_08_الرئيسية
TC_09_الرئيسية
TC_02_فرقك

## "الرئيسية" page
Test Scenario | Test Case ID | Description | pre_condtions | test steps | Expected Result | Actual Result | Status
validate that main pages buttons are working well | TC_01_الرئيسية | validate that main pages buttons are working well | 1-Yallakora application is already installed on an Andriod mobile. 2-the mobile phone is connected to internet connection. 3-Yallakora app is been opened. | press on the main buttons at the bottom of the screen one by one. | user can navigate to main pages successfully | as Expected | pass
check "matches of today" on "main" page | TC_02_الرئيسية | check "the mathes of today" are been dispalyed on main page |  | 1-go to "the mathes of today" section on the main page 2-choose any of the today's matches | 1-the matched are been viewed on the screen 2-the user is been redirected to the match details.
| TC_03_الرئيسية | check the announced mathes on the media against the matched at the app. |  | compare the matches on the app against ones on the media | results are matching
| TC_04_الرئيسية | check the date and time of the match |  | list the date and time of any match and compare it with the actual ones. | date and time are the identical with the actual
| TC_05_الرئيسية | check that user can view "all matches" from its button |  | press on "all matches" button. | user is been redirected of "matched" page and all matches are been displayed successfully
check match details | TC_06_الرئيسية | user can view details about the match "ملخص","التشكيل","دقيقة بدقيقة" |  | press on any match on the screen | user is naivgate to new page with all details about this match and must be there "ملخص","التشكيل","دقيقة بدقيقة" | some of teams haven't "التشكيل" details and "دقيقة بدقيقة" doesn't have any value | fail
check "news" on "main" page | TC_07_الرئيسية | check "news" on "main" page |  | go to "news" section on the main page and choose any one of it. | the chosen news is been displayed successfully with all its details | as Expected | pass
| TC_08_الرئيسية | check that user can view "all news" from its button |  | press on "all news" button. | user is been redirected of "news" page and all news are been displayed successfully
check notifications of the app | TC_09_الرئيسية | a notification send to user about (news) | 1-Yallakora application is already installed on an Andriod mobile. 2-the mobile phone is connected to internet connection. 3-the mobile is on sleep mode 4-there is a recieved notification. | press on that notification | user is been redirected to the Yallakora app and the news page is been opened with the details of this notification.

## "مباريات" page
Test Scenario | Test Case ID | Description | pre_condtions | test steps | Expected Result | Actual Result | Status
check match status | TC_01_مباريات | validate that when match will be played,the date and time are been displayed only | 1-Yallakora application is already installed on an Andriod mobile. 2-the mobile phone is connected to internet connection. 3-Yallakora app is been opened. | 1-press on "مباريات " 2-choose any match will be played. | only date and time of the match will be displayed on the screen. | as Expected | pass
| TC_02_مباريات | validate that when match is live,the word "live" is shown to the user on the screen. |  | 1-press on "مباريات " 2-choose any match is been playing now | "live" word is shown between names of two teams
| TC_03_مباريات | validate that when match is over,the word "over" is shown to the user on the screen. |  | 1-press on "مباريات " 2-choose any match is been played | "finished" word is shown between names of two teams
check the result of the match | TC_04_مباريات | validate that the result is correct |  | 1-press on "مباريات " 2-choose any match is been played or is live now. | the acual and right result is been shown

## "بطولات" page
Test Scenario | Test Case ID | Description | pre_condtions | test steps | Expected Result | Actual Result | Status
check team profile/country | TC_01_بطولات | user can display a details about any team or country he choose | 1-Yallakora application is already installed on an Andriod mobile. 2-the mobile phone is connected to internet connection. 3-Yallakora app is been opened. | 1-press on "بطولات" button. 2-press on "كأس العالم" choice. 3- choose "السنغال" country | new page that contains all details about the national team | as Expected | pass

## "فرقك" page
Test Scenario | Test Case ID | Description | pre_condtions | test steps | Expected Result | Actual Result | Status
validate that addition function for team or country is working | TC_01_فرقك | user can add his/her favorite team/national team to "my teams" | 1-Yallakora application is already installed on an Andriod mobile. 2-the mobile phone is connected to internet connection. 3-Yallakora app is been opened. | 1-press on "فرقك" button 2- press on '+' sign 3-choose from the list "كأس العالم" 4-choose "الأرجنتين" | "الارجنتين" national team is been added to my teams. | as Expected | pass
| TC_02_فرقك | user can delete his/her favorite team/national team from "my teams" |  | 1-press on "فرقك" button 2- press on delete sign next to '+' 3-choose "الأرجنتين" | "الارجنتين" national team is been deleted from my teams.

## "اخبار" page
Test Scenario | Test Case ID | Description | pre_condtions | test steps | Expected Result | Actual Result | Status
check "latest news " on "news" | TC_01_اخبار | user can display latest news and read any of them by choosing one of them. | 1-Yallakora application is already installed on an Andriod mobile. 2-the mobile phone is connected to internet connection. 3-Yallakora app is been opened. | 1-press on "news" button at the bottom of main screen. 2-choose the first news on the new page | a new page will be shown with a full details of the chosen news | as Expected | pass
check "another sports " on "news" | TC_02_اخبار | user can find othe news of different sports otherwise football. |  | 1-press on "news" button at the bottom of main screen. 2-press on "رياضات أخرى" button at the top of the screen | a news about different sports must be shown to the user | most of the shown news are related to football sport,and a little of news about another one or two different sports. | fail

## Bug report
Bug_ID | TC_ID | Description | Pre-conditions | Steps to reproduce | Expected result | Actual result | Attachments | Severity | Priority | Status
B_01 | TC_06_الرئيسية | when user go to match details,it appears three choices to him: "الملخص" ,"التشكيل","دقيقة بدقيقة". "الملخص" show details always about the match, "التشكيل","دقيقة بدقيقة"show details in most matches but not all the matches. | 1-Yallakora application is already installed on an Andriod mobile. 2-the mobile phone is connected to internet connection. 3-Yallakora app is been opened. | 1-press on any match on the screen 2-check the content of "الملخص" ,"التشكيل","دقيقة بدقيقة". sections of different matches. | Every match must have details about "الملخص" ,"التشكيل","دقيقة بدقيقة". | some of matches all details in the subsections, but others don't have "f" details ,and "f" section don't have any information about it at all. |  | mionr | medium | new
B_02 | TC_02_اخبار | when user go to the "رياضات أخرى" section to view other differnet sports without "football game", it still view most news about the football game and rarely about different sports. |  | 1-press on "news" button at the bottom of main screen. 2-press on "رياضات أخرى" button at the top of the screen | a news about different sports must be shown to the user | most of the shown news are related to football sport,and a little of news about another one or two different sports. |  | minor | low | new
B_03 | Exploratory testing | only arabic language is provided and there is no any other language like English |  | check any of app content . | there is an option to choose English language. | only arabic language provided. |  | minor | medium | new
B_04 |  | there are abbrevilations without declaration, and this will confuse any one who isn't familiar with football sport |  | 1-go to "فرقك" page 2-choose one of your favorite team | abbreviation of "ف","ت","ه","ل" are been descrptive at the top page "فوز" ,"تعادل","هزيمة","عدد المباريات". | only abbreviation of "ف","ت","ه","ل" is been shown next to the team name
B_05 |  | five of symobls "ه","ت","ف" are shown with unmatched number of the last actual team matches |  | 1-go to "فرقك" page 2-choose one of your favorite team 3-check matches of team which is already played recently | the five symobls descirbe last matched have been played. | unmatched with the actual matches. |  | major | high | new
B_06 |  | at the "مباريات" page there is a "play" symbol on the top ,when user press on it ,it make him exit from the app without any confirmation message |  | 1-go to "مباريات" page 2-press on the "play" sympol at the top of the page | this symbol must be on all the pages or on the main page only with "exit" labeled button with a confirmation message with "Are you sure to exit"with "yes" and "no" . | the app is been closed |  | minor | high | new
B_07 |  | at the news section ,there isn't any information about the publisher of the chosen news like "job title,his employer" |  | 1-go to "اخبار" 2-choose a random news | details about the news publisher and its profile details. | only his name. |  | minor | high | new
B_08 |  | "bug at design", when user trying to add a fav team , position of "موافق" button is mismatch and it is better to have distinct shape at the end of the page |  | 1-go to "فرقك" page 2-search for "ليفربول team" | "موافق" button is shown with a distinct color at the bottomof the page. | the button is shown at the top ,it isn't obvious to the user. |  | mionr | low | new
B_09 |  | order of "بطولات' isn't correct |  | 1-go to "بطولات" page | the order of "بطولات" must be alphatecially or related to itspopularity or the time. | order of "بطولات" is random. |  | minor | high | new
B_10 |  | when user search for any team or national team, there is no any result. although it is shown in search bar field: "بحث عن فرقة أو منتخب" he must know where this team locate in which "champion". |  | 1-go to "فرقك" page 2-enter "مصر" or "ليفربول" in search bar | "مصر" or "ليفربول" should be shown on the page | unmatched results with names of champions or even no results at all. |  | critical | high | new
B_11 |  | misorder at weeks of "بطولات " and its date |  | 1-go to "بطولات" page 2-choose "الدورى الانجليزى" then "مباريات" 3-choose "الاسبوع السابع" from the top | "الاسبوع السابع" must be in its correct order and contains the correct date. | الاسبوع السادس عشر" is after "الاسبوع السابع" and contains wrong dates |  | critical | high | new
B_12 |  | when user at a match details page and open "دقيقة بدقيقة" then try to go to "التشكيل" , it doesn't respose,and he froced to try many times till to open"التشكيل" |  | 1-press on the first match on the home page 2-press on "دقيقة بدقيقة" then "التشكيل" | user can view "التشكيل" section successfully | user faces difficulties to reach "التشكيل" and can get "التشكيل" after number of trials. |  | minor | medium | new